## WF1 - Order
Workflow 1: Customer Places an Order with a Restaurant
Project | ROS — Restaurant One Solution
Team | Spreadsheet Spartans
Date | 2026-06-18
Tested By | Aman Deep
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Order Date Conversion | Text dates | Date format generated | Conversion failed for some rows | Fail | Invalid date format | String to Date&Time | Fixed
TC-02 | Tax Calculation | Order amount + tax | Correct total | Incorrect total | Fail | Formula issue | Corrected Math Formula | Fixed
TC-03 | Missing Restaurant ID | Null restaurant_id | Invalid order flagged | Not flagged | Fail | Validation missing | Added Rule Engine | Fixed
TC-04 | Negative Order Amount | Negative value entered | Record rejected | Accepted | Fail | Validation missing | Added Rule Engine condition | Fixed
TC-05 | Duplicate Orders | Same order_id repeated | Duplicate removed | Duplicate present | Fail | Duplicate records | Duplicate Row Filter | Fixed
TC-06 | Blank Payment Values | Null payment fields | Default 0 | Null output | Fail | Missing value issue | Missing Value node | Fixed
TC-07 | Future Order Date | Date > current date | Flag for review | Accepted | Fail | Business rule missing | Date validation rule | Fixed
TC-08 | Valid Order | Clean record | Process successfully | Success | Pass | None | N/A | Passed
Total test cases | 8
Bugs found | 7
Bugs fixed | 7
Final status of workflow | Successfully Deployed

## WF2 - Delivery
Workflow 2: Delivery Partner Delivers the Order
Project | ROS — Restaurant One Solution
Team | Spreadsheet Spartans
Date | 2026-06-18
Tested By | Aman Deep
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Order-Delivery Join | Matching records | Joined successfully | Duplicate rows | Fail | Wrong join logic | Updated Joiner | Fixed
TC-02 | Missing Delivery Record | No delivery entry | Retain order | Order dropped | Fail | Inner Join issue | Left Join applied | Fixed
TC-03 | API Amount Calculation | Delivery fee deduction | Correct amount | Incorrect amount | Fail | Formula issue | Updated formula | Fixed
TC-04 | Negative Delivery Charges | Negative charges | Reject record | Accepted | Fail | Validation missing | Rule Engine | Fixed
TC-05 | Duplicate Delivery Entries | Same delivery twice | Single record | Duplicate found | Fail | Duplicate data | Duplicate Row Filter | Fixed
TC-06 | Null Delivery Partner | Missing partner | Flag exception | Passed through | Fail | Validation missing | Rule Engine | Fixed
TC-07 | Delivery Status Generation | Match status | Status assigned | Missing status | Fail | Missing logic | Added Rule Engine | Fixed
TC-08 | Valid Delivery Record | Clean record | Success | Success | Pass | None | N/A | Passed
Total test cases | 8
Bugs found | 7
Bugs fixed | 7
Final status of workflow | Successfully Deployed

## WF3 - Cash-Up Published
Workflow 3: Cash-Up Published to the Finance Team
Project | ROS — Restaurant One Solution
Team | Spreadsheet Spartans
Date | 2026-06-18
Tested By | Aman Deep
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Sales Join | Matching sales | Linked successfully | Missing rows | Fail | Join mismatch | Left Join | Fixed
TC-02 | Expense Join | Matching expenses | Linked successfully | Missing records | Fail | Join mismatch | Join correction | Fixed
TC-03 | Tax Calculation | Tax values present | Correct EOD | Incorrect EOD | Fail | Formula error | Updated formula | Fixed
TC-04 | Missing Sales | Null sales value | Flag exception | Accepted | Fail | Validation missing | Rule Engine | Fixed
TC-05 | Negative Expense | Negative expense | Reject record | Accepted | Fail | Validation missing | Rule Engine | Fixed
TC-06 | Reconciliation Status | Match values | Status generated | Missing status | Fail | Logic missing | Rule Engine | Fixed
TC-07 | Duplicate Cashup Records | Same cashup twice | Unique record | Duplicate found | Fail | Duplicate records | Duplicate Filter | Fixed
TC-08 | Valid Cashup | Complete data | Published | Published | Pass | None | N/A | Passed
Total test cases | 8
Bugs found | 7
Bugs fixed | 7
Final status of workflow | Successfully Deployed

## WF4 - Banking
Workflow 4: Cash-Up Amount Banked by the Designated Employee
Project | ROS — Restaurant One Solution
Team | Spreadsheet Spartans
Date | 2026-06-18
Tested By | Aman Deep
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Banking Join | Cashup + Banking | Correct mapping | Missing matches | Fail | Join issue | Corrected join | Fixed
TC-02 | Banking Variance | Difference amount | Correct variance | Wrong values | Fail | Formula error | Updated formula | Fixed
TC-03 | AM/PM Indicator | Banking period | Correct classification | Null values | Fail | Missing indicator | Added default value | Fixed
TC-04 | Banking Date Validation | Valid date | Accepted | Invalid dates found | Fail | Date quality issue | Date validation | Fixed
TC-05 | Duplicate Banking Record | Same banking_id | Single record | Duplicate present | Fail | Duplicate rows | Duplicate Filter | Fixed
TC-06 | Exception Banking Logic | Unreconciled cashup | Exception flagged | Not flagged | Fail | Missing rule | Rule Engine | Fixed
TC-07 | Null Banked Amount | Missing value | Flag record | Passed through | Fail | Validation missing | Missing Value node | Fixed
TC-08 | Valid Banking Record | Correct data | Banked successfully | Success | Pass | None | N/A | Passed
Total test cases | 8
Bugs found | 7
Bugs fixed | 7
Final status of workflow | Successfully Deployed

## WF5 - Subscription
Workflow 5: Clients Purchase a Subscription with ROS
Project | ROS — Restaurant One Solution
Team | Spreadsheet Spartans
Date | 2026-06-18
Tested By | Aman Deep
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Client Join | Client linked to subscription | Success | Missing records | Fail | Join issue | Updated join logic | Fixed
TC-02 | User Assignment | License assignment | Count users | Incorrect count | Fail | Duplicate users | Duplicate Filter | Fixed
TC-03 | Product Classification | ROS ERP / ROS AI | Correct category | Missing category | Fail | Rule missing | Added Rule Engine | Fixed
TC-04 | Active Subscription | Active flag | Active status | Incorrect status | Fail | Logic issue | Rule correction | Fixed
TC-05 | Missing Subscription Cost | Null cost | Flag record | Accepted | Fail | Validation missing | Rule Engine | Fixed
TC-06 | Negative License Count | Negative value | Reject record | Accepted | Fail | Validation missing | Added business rule | Fixed
TC-07 | Duplicate Subscription | Same subscription_id | Single record | Duplicate found | Fail | Duplicate rows | Duplicate Filter | Fixed
TC-08 | Valid Subscription | Complete record | Subscription activated | Success | Pass | None | N/A | Passed
Total test cases | 8
Bugs found | 7
Bugs fixed | 7
Final status of workflow | Successfully Deployed

## Overall Summary
ROS Project — Overall Testing Summary
Project | ROS — Restaurant One Solution
Team | Spreadsheet Spartans
Date | 2026-06-18
Tested By | Aman Deep
Total test cases run | 40
Total bugs found | 35
Total bugs fixed | 35
Workflows fully passing (of 5) | 5
Overall conclusion | Passed Testing & Ready for Production

## Column Guide
Column Meanings (Reference)
Column | What you write
Test Case ID | A label for the test (e.g. TC-01).
What Was Tested | The specific thing checked (e.g. UK tax calculation for a dine-in order).
Input / Scenario | The data or situation used for the test.
Expected Result | What should happen, according to the rules / logic.
Actual Result | What actually happened when the test was run.
Pass / Fail | Whether the actual result matched the expected result.
Bug Found | If it failed, what was wrong.
Fix Applied | How the problem was corrected.
Final Status | The result after fixing and re-testing.